## Sheet1
Task No. | Task Title | Estimated Duration | Actual Duration | Assigned to
1 | Initiation | 22 | 17.5 | TEAM
1.1 | Github setup | 1 | 1 | TEAM
1.1.1 | Create personal Account | 0.5 | 0.5 | TEAM
1.1.2 | Create team repository and team project | 0.5 | 0.5 | TEAM
1.2 | Team meeting | 1 | 1 | TEAM
1.2.1 | Role assignment | 0.5 | 0.5 | TEAM
1.2.2 | identify programming needs | 0.5 | 0.5 | TEAM
1.3 | Project Planning & Scheduling | 8.5 | 6 | TEAM
1.3.1 | Assignment Distribution | 0.5 | 0.5 | TEAM
1.3.2 | WBS creation | 3 | 2 | Ruochan Wang
1.3.3 | SDLC creation | 3 | 2 | Zhewen Zhang
1.3.4 | gantt Chart creation | 2 | 2 | Ruochan Wang
1.4 | Clarification of deliverables | 0.5 | 0.5 | TEAM
1.5 | Clarification of project purpose | 0.5 | 0.5 | TEAM
2 | System Study | 3 | 2 | TEAM
2.1 | determination of functionality | 1 | 0.5 | TEAM
2.2 | Topic and agent choosing | 1 | 0.5 | TEAM
2.3 | determination of Programming language and platform | 0.5 | 0.5 | TEAM
2.4 | Program sizing | 0.5 | 0.5 | TEAM
3 | detailed Design | 4.5 | 3.5 | Henter, Stephen
3.1 | UI design | 2 | 1 | Henter Yang
3.2 | Core funtionality design | 0.5 | 0.5 | Henter Yang
3.3 | framework | 1 | 1 | Henter Yang
3.4 | Content input | 1 | 1 | Stephen Wang
4 | Development | 36 | 31 | TEAM
4.1 | coding for dialogue | 30 | 25 | Henter Yang, Ruochan Wang, Stephen Wang, Zhewen Zhang
4.2 | Documenting the description of the program process | 3 | 2 | Stephen Wang
4.3 | listing limitations of the program | 1 | 1 | Henter Yang stephen wang
4.4 | README file development | 2 | 3 | Alatar Wu
5 | Implementation | 16.5 | 13.5 | TEAM
5.1 | code testing & debugging | 8 | 7 | Henter Yang, Alatar Wu
5.1.1 | coverage testing | 5 | 3 | Henter Yang, Alatar Wu
5.1.2 | Syntax error correction | 1 | 0.5 | Henter Yang, Alatar Wu
5.1.3 | feasibility modification | 2 | 2 | Henter Yang, Alatar Wu
5.2 | presentation Video development | 8.5 | 6.5 | TEAM
5.2.1 | demo recording & voice recording | 2 | 1 | Stephen Wang, Ruochan Wang
5.2.2 | self-introduction | 0.5 | 0.5 | TEAM
5.2.3 | PM graph development | 2 | 3 | Ruochan Wang
5.2.4 | merging | 2 | 1 | Zhewen Zhang
5.2.5 | subtitling the video | 2 | 1 | Zhewen Zhang
5.3 | project report integration | 0 | 0 | TEAM
6 | Project completion | 0 | 0 | TEAM
6.1 | Submitting the final presentation video & report | 0 | 0 | TEAM
6.2 | Being ready for presentation | 0 | 0 | TEAM